## Sheet1
Bright Coffee Shop Sales Analysis: Project Plan
Project start date : |  |  |  |  | 2026-10-05
# | Phase / Task | Deliverable | Start wk | Weeks | Start date | End date | Status | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | PHASE 1: Data understanding
1.1 | Inspect raw data in Databricks | Stores, date range, hours, products, categories | 1 | 1 | 2026-10-05 | 2026-10-09 | Complete
1.2 | Clean data & fix unit price format | unit_price converted to decimal | 1 | 1 | 2026-10-05 | 2026-10-09 | Complete
2 | PHASE 2: Data preparation & analysis
2.1 | Build sales_final table | Revenue, day/month, time bucket columns | 2 | 1 | 2026-10-12 | 2026-10-16 | Complete
2.2 | Grouped summary query | Summary by date, store, product | 2 | 1 | 2026-10-12 | 2026-10-16 | Complete
2.3 | Additional analysis queries | Avg transaction, trend, weekend vs weekday, mix shift | 2 | 1 | 2026-10-12 | 2026-10-16 | Complete
2.4 | Export final dataset to CSV | sales_final.csv | 3 | 1 | 2026-10-19 | 2026-10-23 | Complete
3 | PHASE 3: Dashboards
3.1 | Excel dashboard + store map | Excel_Dashboard.xlsx | 3 | 1 | 2026-10-19 | 2026-10-23 | Complete
3.2 | Power BI dashboard + coffee theme | Power BI .pbix file | 3 | 2 | 2026-10-19 | 2026-10-30 | Complete
3.3 | Looker Studio dashboard | Shareable dashboard link | 4 | 1 | 2026-10-26 | 2026-10-30 | In progress
4 | PHASE 4: Insights & reporting
4.1 | Validate key insights against data | Verified findings list | 4 | 1 | 2026-10-26 | 2026-10-30 | In progress
4.2 | Write README | README.md | 4 | 1 | 2026-10-26 | 2026-10-30 | Complete
4.3 | Prepare CEO presentation | PowerPoint deck | 5 | 1 | 2026-11-02 | 2026-11-06 | Not started
5 | PHASE 5: Submission
5.1 | Final review & submit | SQL script, dashboards, README, deck | 5 | 1 | 2026-11-02 | 2026-11-06 | Not started
Formulas:
Start date = F2+([Start wk]-1)*7
End date = [Start date]+[Weeks]*7-3